## Slide 1: Opportunity: Controller Roster Review
Low Medium High
Benefits
$0 - $500,000 $500,000 - $1M >$1M
N/A Low Medium High Extreme
Cost reduction
Increased productivity
Customer Satisfaction
Risk to be mitigated
Key Stakeholders/SME’s
Dugald Bell
Nathan Hill
Andrew Barwise
Darko Nenadic
Human Resources
Operational Improvement BP
Context
There is currently 22 controllers and 2 team leaders whose responsibility is to write switching programs for planned work and provide relief to the Control Room during busy periods.
Initiator: Dugald Bell
Opportunity
The opportunity is three fold. Firstly, develop a roster that meets current operational requirements and is aligned to the control room roster (does that include location yes it does). Secondly, drive cultural changes that encourages camaraderie and standardise working arrangements. Thirdly allow program writers the time to complete the training required to work in the control room. A new roster must be designed to have designated training days for each employee.
Organisational / Business Impact
Resource Requirements (FTE/SME)
1
10+
5-10
Project Duration
6 – 12 months
Up to 6 months
>12 months
Business Problem
The current roster does not meet the current work requirements (what requirements?). It is not aligned to the control room roster as the Controllers EA is for 9.5 hrs whilst the Control Room operates in 12.5 hr shifts and does not account for the fact that controllers currently have the flexibility to nominate their chosen work site. The ability of Controllers to dictate their worksite is unfeasible. The current roster is creating a division within the controllers whilst also preventing controllers from spending enough time in the control room. It has been stated that the controllers need to spend more time in the control room to allow skill retention and development.
Currently 11 controllers do not have the required competencies and therefore can only work as Program Writers. There is no tolerance in the current roster to allow for the necessary training.
Investment Requirements (funding)
$0 - $0.5M $0.5 - $1M > $1M
Proposed Sponsor: Dugald Bell
OI BP: Andrew Barwise
Date: 24/08/2022
EDM:
L
M
H
Alignment with
AO 3-year plan
Reliable
Affordable
Operational Excellence
Safe
People
Alignment with Values
Safety First
Customer Focus
Be Bold
Teamwork
Pillar fit
1. Optimise core operations
2. Strengthen the culture
3. Operationalise & scale future capabilities
Fits under which 3-year plan project?
(See EDM59768417)
Low Medium High
Dependencies or other aligned initiatives